CRM Project

Architecture, Tech Stack & Development Plan

Version 1.0

CRM System for ISEET Digital Transformation

Date: 18/4/2026

presented by: Hamzah Ghnimat

position: BA

# Table of Contents

1.  Introduction…………………………………………………………………………………………….	3

1.1  Purpose of This Document………………………………………………………………………………	3

1.2  Project Background………………………………………………………………………………………	3

1.3  Document Structure……………………………………………………………………………………...3

2.  Definitions………………………………………………………………………………………………	4

3.  Scope…………………………………………………………………………………………………..	4

3.1  In Scope…………………………………………………………………………………………………...	.4

3.2  Out of Scope………………………………………………………………………………………………	5

4.  Executive Summary………………………………………………………………………………….	5

5.  System Architecture…………………………………………………………………………………..	6

5.1  Architecture Overview…………………………………………………………………………………...	6

5.2  Integration Points………………………………………………………………………………………...	7

6.  Technology Stack……………………………………………………………………………………..7  Development Environment Setup………………………………………………………………………	9

7.1  Prerequisites……………………………………………………………………………………………...	9

7.2  Setup Steps……………………………………………………………………………………………...	10

8.  Development Plan — Modules, Timeline & Priorities……………………………………………	11

8.1  MVP Scope Definition………………………………………………………………………………...	11

8.2  Detailed Module Plan with Timeline…………………………………………………………………………………………………...	11

9.  Sprint Timeline Summary…………………………………………………………………………..	13

10.  Risks & Mitigation………………………………………………………………………………….	14

11.  Recommended Next Steps………………………………………………………………………..	15

# Introduction

ISEET is a technology consulting firm based in Amman, Jordan, specializing in digital transformation for organizations across various sectors. As part of its own digital growth, ISEET identified the need for a structured Customer Relationship Management (CRM) system to centralize client data, streamline internal communication, and improve overall service delivery. This document is prepared by the Business Analyst and serves as the technical planning bridge between the completed analysis documentation — the BRD, FRD, and SRS — and the Engineering and Development phase, covering the system architecture, technology stack, development environment, and a prioritized module plan.

# Definitions

The following terms are used throughout this document. Understanding these definitions is essential for all stakeholders engaging with the technical content.

CRM (Customer Relationship Management): A system used to manage a company's interactions with current and potential customers by centralizing client data, communications, and activity history in one place.

API (Application Programming Interface): A set of rules that allows two software systems to communicate with each other. In this project, APIs connect the ISEET public website to the internal CRM portal via HTTP requests.

RBAC (Role-Based Access Control): A security model that restricts system access based on the user's assigned role. In this CRM, roles are: Manager, Employee, and Client — each with specific permissions.

MVP (Minimum Viable Product): The smallest functional version of the system that delivers core value. The MVP must be fully operational before optional or advanced features are developed.

SMTP (Simple Mail Transfer Protocol): The standard protocol used for sending emails. In this project, SMTP serves as the gateway between the CRM chat interface and the client's email inbox.

MVC (Model-View-Controller): The software design pattern used by Laravel. It separates application logic (Model), user interface (View), and request handling (Controller) for cleaner and maintainable code.

Sprint: A fixed time period (typically 1–2 weeks) in Agile development during which a defined set of features or modules is planned, built, and tested.

ERD (Entity Relationship Diagram): A visual representation of the database structure showing all data tables and the relationships between them.

# Scope

This section defines the boundaries of the ISEET CRM project for this phase of development, clearly identifying what is included and what is intentionally excluded.

## In Scope

The current phase covers the full development of the dual-platform CRM system, including the public ISEET website (Talk to Us, Consultations, Job Opportunities), the internal CRM portal with role-based dashboards for Managers and Employees, automated client profile creation, two-way email communication, consultation scheduling, meeting notes management, AI-driven sales forecasting, Google Maps integration, cloud deployment on AWS or Azure, and bilingual support for English and Arabic.

## Out of Scope

The following items are explicitly excluded from this project phase. They may be considered in a future release:

Mobile Application  —  No iOS or Android app will be developed in this phase. The system is web-only.

Payment Processing  —  The CRM will not handle any financial transactions, invoicing, or payment gateway integration.

HR & Salary Management  —  Employee management, payroll, and internal HR workflows are outside the scope of this system.

Third-Party Social Media Integration  —  No direct integration with LinkedIn, Twitter/X, Facebook, or other social platforms is planned for this phase.

Full ERP Integration  —  The CRM is not integrated with any external ERP (Enterprise Resource Planning) system in this phase.

Advanced Analytics Dashboard  —  While the AI module provides service-usage forecasting, a full business intelligence or analytics dashboard (e.g., Power BI integration) is not in scope.

# Executive Summary

Based on a thorough review of the BRD, FRD, and SRS documentation for the ISEET CRM project, this document defines the recommended system architecture, technology stack, development environment setup, and a prioritized MVP development plan. This deliverable serves as the technical handoff bridge between the Business Analysis phase and the Engineering phase.

The ISEET CRM is a dual-platform web system consisting of a customer-facing public website and an internal CRM portal. It supports three user roles (Manager, Employee, Client) and integrates features including client profile management, email-based communication, consultation scheduling, AI-driven sales forecasting, and job opportunity management.

# System Architecture

The ISEET CRM adopts a classic three-tier client-server architecture with a clear separation of concerns across four distinct layers.

## Architecture Overview

| ISEET CRM — Layered Architecture |  |
| --- | --- |
| Layer 1 Presentation | Public ISEET Website + Internal CRM Portal HTML5 · CSS3 · JavaScript (Vanilla / jQuery) ¦ Rendered server-side by Laravel Blade - Responsive UI supporting Arabic (RTL) and English (LTR) - Role-specific dashboards (Manager / Employee / Client) - Google Maps embed for client location rendering |
| Layer 2 Application | Laravel (PHP 8.x) — REST API Backend MVC Architecture · Eloquent ORM · Laravel Sanctum Authentication - RBAC enforced via middleware (Manager / Employee roles) - API endpoints: HTTP POST (submit data) / HTTP GET (retrieve data) - SMTP integration for email-to-CRM chat gateway - AI module: sales forecasting logic (Python microservice or Laravel-based) - Real-time notifications (Laravel Events + Broadcasting / Pusher) |
| Layer 3 Data | MySQL 8.x — Relational Database Managed via Laravel Migrations & Eloquent ORM - Core entities: clients, users, meetings, emails, opportunities, projects, reports - Auto-sync: Employee notes → Manager Reports (trigger/event-based) |
| Layer 4 Cloud | Cloud Hosting — AWS or Microsoft Azure Target Uptime: 99.9% SLA - App server: EC2 (AWS) or App Service (Azure) - Database: RDS MySQL (AWS) or Azure Database for MySQL - File Storage: S3 or Azure Blob (for document attachments) - SSL/TLS via Let's Encrypt or ACM — end-to-end encryption enforced |

## Integration Points

The following external integrations are required based on the FRD and SRS specifications:

| Integration | Tool / Service | Purpose |
| --- | --- | --- |
| Google Maps API | Google Maps JS API | Render client location on profile page |
| Email Gateway | SMTP (Laravel Mailable) | Two-way email-to-CRM chat communication |
| Push Notifications | Pusher / Laravel Echo | Real-time consultation alerts to employees |
| AI Forecasting | Python (scikit-learn) or Laravel Logic | Sales probability % per client |
| WhatsApp / Email Share | WhatsApp API / Mailable | Share AI forecast reports to employees |

# Technology Stack

The following technology stack is recommended based on the architecture defined in the BRD, FRD, and SRS documents. All choices align with the Laravel/PHP + MySQL + HTML/CSS/JS stack specified in the architecture diagram.

| Category | Technology | Justification |
| --- | --- | --- |
| Backend Framework | Laravel 10.x (PHP 8.2) | Specified in SRS architecture diagram. Provides Eloquent ORM, RBAC middleware, Mailable, and Events out of the box. |
| Frontend | HTML5, CSS3, JavaScript | As defined in FRD. Blade templating for SSR. JavaScript handles Google Maps embed, real-time chat UI, and dynamic notifications. |
| Database | MySQL 8.x | Specified in SRS. Relational structure suits client profiles, meetings, email logs, and reports. Handled via Laravel Migrations. |
| Authentication | Laravel Sanctum + RBAC | Satisfies NFR: MFA-ready, session-based tokens. RBAC enforces Manager vs. Employee access control. |
| Email Service | SMTP via Laravel Mailable | Bridges CRM chat with client email inbox. Satisfies BRD email integration requirement. |
| Maps | Google Maps JavaScript API | SRS specifies Google Maps for client location rendering on profile page. |
| Notifications | Laravel Broadcasting + Pusher | Delivers real-time alerts (< 5 sec per NFR) when consultations are booked or profiles are accessed. |
| AI Module | Python (scikit-learn) Microservice | Processes 'All Meetings' data to return service utilization probability. Modular per NFR scalability requirement. |
| Cloud Hosting | AWS (EC2 + RDS + S3) | Satisfies 99.9% uptime SLA. RDS for MySQL, EC2 for Laravel app, S3 for file storage. |
| Version Control | Git + GitHub / GitLab | Standard industry practice. Enables branching strategy, code review, and CI/CD pipeline integration. |
| Dev Environment | XAMPP / Laravel Sail (Docker) | Local development. Sail provides Docker-based parity with production environment. |
| API Testing | Postman | For testing all HTTP POST/GET endpoints during development phases. |

# Development Environment Setup

This section provides a step-by-step guide for the development team to configure a fully operational local environment before writing any code.

## 7.1 Prerequisites — Software to Install

| Tool | Version | Purpose |
| --- | --- | --- |
| PHP | 8.2+ | Required by Laravel 10.x backend |
| Composer | Latest | PHP dependency manager for Laravel packages |
| Laravel Installer | 10.x | Scaffolds the project structure |
| MySQL Server | 8.0+ | Local database server (or use RDS in staging) |
| Node.js + NPM | 18.x LTS | Required for Laravel Mix / asset compilation |
| Git | Latest | Version control — clone from GitHub/GitLab repo |
| Postman | Latest | API endpoint testing during development |
| XAMPP or Docker (Sail) | Latest | Local server environment (Apache + PHP + MySQL) |
| VS Code | Latest | Recommended IDE with PHP Intelephense extension |

## 7.2 Setup Steps

Step 1: Clone the Repository

git clone https://github.com/iseet/crm-system.git cd crm-system

Step 2: Install PHP Dependencies

composer install

Step 3: Configure Environment Variables

cp .env.example .env php artisan key:generate  # Edit .env: Set DB_DATABASE, DB_USERNAME, DB_PASSWORD, # MAIL_HOST, MAIL_PORT, PUSHER_* keys, GOOGLE_MAPS_API_KEY

Step 4: Run Database Migrations & Seeders

php artisan migrate --seed # Creates all tables and inserts test users (admin, employee, demo client)

Step 5: Install Frontend Assets

npm install npm run dev

Step 6: Launch Local Server

php artisan serve # Application available at: http://localhost:8000

Step 7: Verify Setup

Open Postman → Test GET /api/clients Login at /login with seeded credentials Confirm Manager dashboard shows: Reports, Projects, AI, Schedule Meetings

# Development Plan — Modules, Timeline & Priorities

The following plan is structured around an MVP-first approach. Priority 1 items are essential for the system to function at its core. Priority 2 items extend functionality. Priority 3 items are the optional/advanced features defined in the BRD.

## MVP Scope Definition

The MVP must deliver the following capabilities before any optional features are developed:

- Client data submission via 'Talk to Us' form on ISEET website — stored in MySQL via Laravel API

- Automatic CRM profile creation per client

- Authenticated login for Manager and Employee (RBAC enforced)

- Client profile page displaying all required fields

- Two-way email communication from CRM chat window

- Consultation scheduling and meeting notes capture

- Employee notes auto-synced to Manager Reports

## Detailed Module Plan with Timeline

| # | Module / Feature | Sprint | Duration | Priority | Key Deliverables |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Setup & Environment | Sprint 0 | Week 1 | P1 | Repo init, env config, migrations, seeding, CI pipeline setup |
| 2 | Database Schema Design | Sprint 0 | Week 1 | P1 | ERD finalization, all migration files, RBAC roles & permissions |
| 3 | Authentication (Login / RBAC) | Sprint 1 | Week 2 | P1 | Login page, Sanctum tokens, role middleware, redirect by role |
| 4 | ISEET Homepage — Talk to Us | Sprint 1 | Weeks 2–3 | P1 | 'Talk to Us' form, HTTP POST to Laravel, MySQL insert, success response |
| 5 | CRM — Client Profile Creation | Sprint 1 | Week 3 | P1 | Auto-profile creation on form submit, profile list view in CRM |
| 6 | Client Profile Page (Full View) | Sprint 2 | Week 4 | P1 | Display: Name, Company, Sector, Country, Email, Phone, Location, Meetings |
| 7 | Manager Dashboard | Sprint 2 | Weeks 4–5 | P1 | Reports panel, Schedule Meetings panel, Projects panel — RBAC protected |
| 8 | Employee Dashboard | Sprint 2 | Week 5 | P1 | Client list, profile access, report submission to Manager Reports |
| 9 | Email-to-CRM Chat Gateway | Sprint 3 | Weeks 5–6 | P1 | SMTP send from CRM, receive replies, store thread in MySQL, display in chat UI |
| 10 | Consultation Module | Sprint 3 | Week 6 | P2 | 'Consultations' button on ISEET, video embed, time slot selection, notification |
| 11 | Consultation Notifications | Sprint 3 | Week 7 | P2 | Real-time alert (Pusher) to employee when client books consultation |
| 12 | Meeting Notes & All Meetings | Sprint 4 | Week 7 | P2 | Notes form, post-meeting record, auto-sync to Manager Reports |
| 13 | Google Maps Integration | Sprint 4 | Week 8 | P2 | Client location stored in DB, Google Maps JS API rendered on profile |
| 14 | Job Opportunities Module | Sprint 4 | Week 8 | P2 | Employee adds jobs (HTTP POST), displayed on ISEET homepage (HTTP GET) |
| 15 | Manager Projects Module | Sprint 5 | Week 9 | P2 | Projects CRUD for manager, listed on dashboard |
| 16 | AI Sales Forecasting Module | Sprint 5 | Weeks 9–10 | P3 | Process All Meetings data, return % score per client, display on Manager AI panel |
| 17 | Report Sharing (Email / WhatsApp) | Sprint 5 | Week 10 | P3 | Share AI forecast report via email or WhatsApp link |
| 18 | Reminders & Alerts | Sprint 6 | Week 11 | P3 | Automated reminders for follow-ups, opportunities, and meetings |
| 19 | Arabic (RTL) Language Support | Sprint 6 | Week 11 | P3 | Full RTL layout, Arabic translations, locale switching |
| 20 | Testing, QA & Bug Fixes | Sprint 6 | Week 12 | P1 | Unit tests, integration tests, Postman API test suite, UAT with stakeholders |
| 21 | Deployment to Cloud (AWS/Azure) | Sprint 6 | Week 12 | P1 | Production deployment, SSL, DNS, RDS setup, monitoring dashboard |

Priority Legend:  P1 = MVP / Critical    P2 = Important / Phase 2    P3 = Optional / Phase 3

# Sprint Timeline Summary

| Sprint | Timeline | Focus & Deliverables |
| --- | --- | --- |
| Sprint 0 | Week 1 | Foundation: Repo setup, DB schema, environment configuration, seeding |
| Sprint 1 | Weeks 2–3 | Core MVP: Authentication, ISEET website Talk to Us form, CRM profile creation |
| Sprint 2 | Weeks 4–5 | Dashboards: Full client profile view, Manager dashboard, Employee dashboard |
| Sprint 3 | Weeks 5–7 | Communication: Email-CRM gateway, Consultation module, real-time notifications |
| Sprint 4 | Weeks 7–8 | Enhancements: Meeting notes, Google Maps, Job Opportunities module |
| Sprint 5 | Weeks 9–10 | Advanced: Manager Projects, AI forecasting, report sharing (Email/WhatsApp) |
| Sprint 6 | Weeks 11–12 | Polish: RTL/Arabic, Reminders, QA/UAT, Cloud deployment |

Total Estimated Duration: 12 Weeks  (3 Months)

# Risks & Mitigation

| Risk | Level | Mitigation Strategy |
| --- | --- | --- |
| AI module complexity exceeds initial estimates | High | Deliver AI as a stub (mock percentage) in MVP; replace with real model in Phase 3 (Sprint 5). |
| SMTP/email gateway delivery delays | Medium | Use a reliable third-party SMTP provider (Mailgun / SendGrid) with retry logic and logging. |
| Google Maps API quota limits | Low | Monitor usage in Cloud console. Cache client coordinates in MySQL to reduce API calls. |
| Scope creep from stakeholders mid-development | Medium | All change requests must pass through BA review and be assessed against the BRD before acceptance. |
| Insufficient cloud budget for AWS/Azure | Medium | Start on AWS Free Tier; plan production upgrade. Alternatively, use Hostinger VPS as a cost-efficient MVP host. |

# Recommended Next Steps

1.  Share this document with the technical lead and development team for review and feedback.

2.  Finalize the ERD (Entity Relationship Diagram) based on the DB schema outlined in this plan.

3.  Set up the Git repository with branch strategy: main, develop, feature/* branches.

4.  Conduct a Sprint 0 kickoff meeting — align the team on the tech stack, environment, and Sprint 1 scope.

5.  Obtain Google Maps API key and SMTP credentials before Sprint 3 begins.

6.  Schedule a UAT review session with ISEET stakeholders at the end of Sprint 6 (Week 12).